## Title Page
Test Plan
NAB Credit Card Payments
Version History
| Date | Version | Author | Changes
| 2017-07-10 | 1 | Danila Tatsenko | Initial document
Distribution
The information in this document is the property of AgilityCIS Ltd. Without the written consent of AgilityCIS, no part of this document may be copied, reprinted or reproduced by any means, electronically or otherwise, nor must the contents of this document or any method, procedure or technique described therein be disclosed to any third party.

## NAB CreditCards
Test (Client / Job Code)
System Tests
Tested by | Danila Tatsenko
Developer
Database | nz-sql2014
TESTCASE 1 |  | Engage Configuration
Business/Functional Requirements
Ref.: Engage Technical Design Specofocation - MM NAB v1.1 - 4.6.Engage Configuration
Settings/Pre Conditions
1. Engage Administration Console has been launched
Test ID | Testers | Scenarios | Expected Results | Actual Results | Status | Defect description | Testers comments | Defect Status | Severity | Priority
NAB_001 |  | Steps: 1. Navigate to Options > System > Maintenance 2. On the left list choose Accounts Receivebale 3. On the right list choose Receipt Batch Type 4. Press OK | 1. Window Receipt Batch Type appears 2. Item WEB exists and has the following properties: * Batch Type Description - Web Payments *Active - (ticked) 3. Item IVR exists and has the following properties: * Batch Type Description - IVR Payments *Active - (ticked) |  | PASS
NAB_002 |  | Steps: 1. Navigate to Options > System > Maintenance 2. On the left list choose Accounts Receivebale 3. On the right list choose Adjustement Reason 4. Press OK | 1. Window Adjustement Reason appears 2. Item REFUND_CC exists and has the following properties: * Adjustment Reason Description - Refund – Credit Card * Statement Description - Refund – Credit Card * Cust Transaction Multiplier - Increases Customer Balance * User Select - (ticked) *Active - (ticked) 3. Item CC_CHGBCK exists and has the following properties: * Adjustment Reason Description - Credit Card – Chargeback * Statement Description - Refund – Credit Card Payment Reversal * Cust Transaction Multiplier - Increases Customer Balance * User Select - (Unticked) *Active - (ticked) 4. Item CC_ERRCOR exists and has the following properties: * Adjustment Reason Description - Credit Card – Error Correction * Statement Description - Refund – Credit Card Payment Reversal * Cust Transaction Multiplier - Increases Customer Balance * User Select - (Unticked) *Active - (ticked) |  | PASS
NAB_003 |  | Steps: 1. Navigate to Options > System > Scheduled Tasks 2. On the Scheduled Task tree expand nodes Active > Workflow | 1. Task Credit Card Refunds to be Processed exists 2. The task has description: Schedule to generate activities for all customers who had a credit card refund adjustment approved from the previous business day. 3. The task has been scheduled for Every weekday at 6 am |  | PASS
TESTCASE 2 |  | Import online credit card payments via the ‘Import NAB Multi Account file’ interface
Business/Functional Requirements
User is able to import Multi-Account Transaction Report file (*.txt) through interface Import NAB Multi-Account files
Settings/Pre Conditions
1. Engage Administration Console has been launched
Test ID | Testers | Scenarios | Expected Results | Actual Results | Status | Defect description | Testers comments | Defect Status | Severity | Priority
NAB_004 |  | Verify that Interface is exist, and user is able to run Inteface with essential elements on the page Steps: 1. Navigate to Options > System > Interfaces 2. In the left Interface Category list choose Banking 3. In the right list choose Import NAB Multi-Account Files 4. Click OK | 1. New webpage Import NAB Multi-Account files is opened 2. There are following enabled elements on the page: - checkbox Commit - text field Email Exceptions to - button Browse, which opens dialog window Open - button Import |  | PASS
Settings/Pre Conditions
1. Engage Administration Console has been launched 2. New webpage Import NAB Multi-Account files has been opened
Test ID | Testers | Scenarios | Expected Results | Actual Results | Status | Defect description | Testers comments | Defect Status | Severity | Priority
NAB_005 |  | Verify that NAB Transaction file with credit cards payments only can be imported and properly processed by Engage. File: NAB File (NAB005_20170705_001.txt) created 04 July 2017 at 10:45:59 for Jacana Energy (client ID - NTA08, BSB - 085933, account number - 742637203) contains 2 detail records for normal succesful payment trasactions: 1) 1. Customer Account Number (Bpay) - 10132695114 2. Payment Intsruction - 05 (Payment) 3. Masked credit card number - MC552350...849 4. Transaction ref number 2 - PBW5001 5. Error Correction Reason - 000 6. Amount - $100.56 7. Payment Date - 15 June 2017 8. Payment Time - 16:54:32 9. Bank Trasaction ID - NAB4321 2) 1. Customer Account Number (Bpay) - 1011128319 2. Payment Intsruction - 05 (Payment) 3. Masked credit card number - MC552387…005 4. Transaction ref number 2 - PBP5002 5. Error Correction Reason - 000 6. Amount - $50 7. Payment Date - 2 July 2017 8. Payment Time - 08:54:23 9. Bank Trasaction ID - NAB1445 Steps: 1. Click Browse on interface webpage and choose file NAB005_20170705_001.txt 2. Tick Commit and click Import | 1. On the interface webpage appears message about successful import: Success! Successfully imported NAB005_20170705_001.txt 2. There is a posted receipt in Transaction list of each customer mentioned in the file (account num: 1013269511) with following properties: 2.1 type of payment mentioned in description - WEB 2.2 amount - $100.56 2.3 transaction date- 15/06/2017 2.4 notes - reference 10132695114, external reference NAB4321, number of credit card 552350...849, type of card Mastercard |  | PASS |  | Positive testing NB: Bank Transaction ID must be unique for ROS! For regression testing this parametr must be changed in ALL sample test files which contain new payments (05) otherwise records won't be created in the system
NAB_006 |  | Verify that receipts will only be created where the “Bank Transaction ID” does not yet exist against another WEB or IVR payment in ROS. File: NAB File (NAB005_20170705_002.txt) with the same content like Test case #NAB_005 Steps: 1. Click Browse on interface webpage and choose file NAB005_20170705_002.txt 2. Tick Commit and click Import | 1. On the interface webpage appears message about successful import: Success! Successfully imported NAB005_20170705_002.txt 2. No reciepts were created in database |  | PASS |  | The better way to check that to use SQL Query: SELECT * FROM ar_receipt
NAB_007 |  | Verify ability to distinguish card types based on the information from the Transaction Reference 3 field of the Multi Account file File: NAB File (NAB005_20170705_003.txt) contains only correct payments with different types of credit cards (excl. JCB, DC) Steps: 1. Click Browse on interface webpage and choose file NAB005_20170705_003.txt 2. Tick Commit and click Import | 1. On the interface webpage appears message about successful import: Success! Successfully imported NAB005_20170705_003.txt 2. In Transaction list of each customer reciepts appear with masked credit card number and type mentioned in field Notes |  | PASS
NAB_008 |  | Verify ability to distinguish online payments (PBW) from other payment types on customer account File: NAB File (NAB005_20170705_004.txt) contains different types of Source (PBW, PBP, DPP, API, BPY). If a Source is not supported, an email will be sent to the email to the email addresses configured on the “NAB_NOTIF_EMAIL” system parameter. Steps: 1. Click Browse on interface webpage and choose file NAB005_20170705_004.txt 2. Tick Commit and click Import | 1. On the interface webpage appears message about successful import: Success! Successfully imported NAB005_20170705_004.txt 2. Only PBP and PBW records were processed and turned into receipts (6 from 10). 3. All payments begining with PBW (Online/Web payment channel) have note WEB in description in Transaction list (for customers: 10106955148, 10132695114) 4. An error email was recieved |  | PASS
NAB_009 |  | Verify that Refund transactions on Online payments from the NAB Multi Account file will be ignored File: NAB File (NAB005_20170705_005.txt) contains different types of payments (PBW, PBP, DPP, API, BPY) with different payment instruction including "25" which should be ignored. Steps: 1. Click Browse on interface webpage and choose file NAB005_20170705_005.txt 2. Tick Commit and click Import | 1. On the interface webpage appears message about successful import: Success! Successfully imported NAB005_20170705_005.txt 2. Only PBP and PBW records were processed and turned into receipts (4 from 10). Records with payment instruction code 25 were skipped |  | PASS
NAB_010 |  | Verify ability to identify Online payments (payment instruction Type=05) with Error correction Reason and put it in the Transaction list as CC_ERRCOR adjustment. File: NAB File (NAB005_20170705_006.txt) contains records with different payment instruction. Some of payments have Error Correction Reason codes differ from "000" Steps: 1. Click Browse on interface webpage and choose file NAB005_20170705_006.txt 2. Tick Commit and click Import | 1. On the interface webpage appears message about successful import: Success! Successfully imported NAB005_20170705_006.txt 2. Only PBP and PBW records were processed. Online payments with instruction type=05 and error correction reason <>000 will be put in Engage as CC_ERRCOR adjustments (Credit Card Payment Reversal). The reason of these adjustments is shown in description column in Transaction list and couldn't be changed by user. |  | PASS
NAB_011 |  | Verify ability to identify Chargebacks on Online payments (using the Transaction Type) from the NAB Multi Account file. File: NAB File (NAB005_20170705_007.txt) contains records with different payments (sources and instruction types). Online payments and payments by phone which have instruction type 35 (chargeback) should dishonour original payment. The ‘Bank Transaction ID’ field will be used as the reference field to identify the original payment. | 1. On the interface webpage appears message about successful import: Success! Successfully imported NAB005_20170705_007.txt 2. In Transaction List appears new adjustments for chrageback (e.g. customer 1013269511). Field Description contains "Adjust - Credit Card Payment Reversal" and field Notes contains concatenated string with reason, external reference,credit card number. External service - Bank Transaction ID for original payment. |  | PASS
NAB_012 |  | Verify ability to identify Chargebacks on Online payments (using the Transaction Type) from the NAB Multi Account file. File: NAB File (NAB005_20170705_008.txt) contains records instruction type 35 (chargeback) but ‘Bank Transaction ID’ has value which doesn't exist in the system. | 1. On the interface webpage appears message about successful import: Success! Successfully imported NAB005_20170705_008.txt 2. In Transaction List appears new adjustments for chrageback (e.g. customer 1014978210) despite that original payment couldn't be matched to the chargeback transaction with Bank Transaction ID |  | PASS
NAB_013 |  | Verify ROS will automatically add the double posting in the Pronto Interface file for Chargebacks. Steps: 1. Navigate to Options > System > Reports 2. In the left Report Category list choose Finance 3. In the right list choose General Ledger Pronto Detail Report 4. Click OK | 1. Report | 1. URL http://nz-sql2012:8085/ReportServer/Pages/ReportViewer.aspx?/Reports/ReportsTest/JACANA/GLProntoDetail&rs:Command=Render 2. Message An error has occurred during report processing. (rsProcessingAborted) Cannot create a connection to data source 'ds_engage_sql'. (rsErrorOpeningConnection) For more information about this error navigate to the report server on the local server machine, or enable remote errors | PASS
NAB_014 |  | Verify ability to trigger an email (system parametr NAB_NOTIF_EMAIL) to the Jacana Support team (and other nominated email addresses) in case the Multi Account file contains payments with Transaction Reference 2 beginning with codes differ from ‘BPY’, ‘PBP’, ‘PBW’ NAB File (NAB005_20170705_009.txt) contains different types of Source (PBW, PBP, DPP, API, BPY). | The email will have the subject of “Multi-Account File Contained Unsupported Source Codes” and have the following body: The following unsupported Source Codes have been received from NAB - <Unsupported Source Code list from file>. Multi-Account file: <Filename> Database: <Database Name> Date: DD/MM/YYYY Resolution: Review Multi-Account file. Contact payment interface provider to understand why we have received the additional codes. (The current implementation supports payments with codes 'BPY', 'PBW', and 'PBP' only on the Multi-Account file) |  | PASS
NAB_015 |  | Verify the Interface will raise error message about missed fields: 1. NAB005_20170705_010.txt has missed Transaction reference numbers (Customer Account Number) 2. NAB005_20170705_011.txt has records with missed Payment Instruction Type 3. NAB005_20170705_012.txt has records with missed Transaction reference number 2 (source) 4. NAB005_20170705_013.txt has has record with missed Date of payment 5. NAB005_20170705_014.txt has has record with missed Amount of payment | 1. Successfully imported NAB005_20170705_010.txt and record with missed customer account number was put into suspended account in ROS 2. Successfully imported NAB005_20170705_011.txt and record with missed Payment Instruction Type was ignored 3. Successfully imported NAB005_20170705_012.txt and records with missed Transaction reference number 2 (source) were ignored 4. Validation Errors Line: 3 - Field: Payment Date - Error: Invalid Payment Date 5. Validation Errors Line: 6 - Field: Receipt Creation - Error: Invalid Receipt Amount |  | PASS
TESTCASE 3
Business/Functional Requirements
Settings/Pre Conditions
Test ID | Testers | Scenarios | Expected Results | Actual Results | Status | Defect description | Testers comments | Defect Status | Severity | Priority
NOT STARTED
NOT STARTED
NOT STARTED
NOT STARTED
Settings/Pre Conditions
Test ID | Testers | Scenarios | Expected Results | Actual Results | Status | Defect description | Testers comments | Defect Status | Severity | Priority
NOT STARTED
NOT STARTED
NOT STARTED
NOT STARTED
NOT STARTED
NOT STARTED
NOT STARTED
NOT STARTED
NOT STARTED
NOT STARTED
TESTCASE 4
Business/Functional Requirements
Settings/Pre Conditions
Test ID | Testers | Scenarios | Expected Results | Actual Results | Status | Defect description | Testers comments | Defect Status | Severity | Priority
[5 empty] | NOT STARTED |  | May need to update once the functionality has been confirmed.
NOT STARTED
NOT STARTED
NOT STARTED
Settings/Pre Conditions
Test ID | Testers | Scenarios | Expected Results | Actual Results | Status | Defect description | Testers comments | Defect Status | Severity | Priority
NOT STARTED
NOT STARTED
NOT STARTED
NOT STARTED
NOT STARTED
NOT STARTED
NOT STARTED
NOT STARTED
NOT STARTED
NOT STARTED
TESTCASE 5
Business/Functional Requirements
Settings/Pre Conditions
Test ID | Testers | Scenarios | Expected Results | Actual Results | Status | Defect description | Testers comments | Defect Status | Severity | Priority
NOT STARTED
NOT STARTED
NOT STARTED
NOT STARTED
NOT STARTED
NOT STARTED
NOT STARTED
NOT STARTED
NOT STARTED
NOT STARTED

## NAB DATA
FILE NAME | Record Type | Source Identifier | Transaction reference number (Customer Account Number) | Payment Instruction Type | Transaction reference number 2 | Transaction reference 3 | Error Correction reason | Amount | Payment Date | Payment Time | Settlement date | Bank Transaction ID | Authorisation Code | Original Reference | Filler
|  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
| 2 | 10 | 20 | 2 | 21 | 21 | 3 | 12 | 8 | 6 | 8 | 30 | 6 | 20 | 50
NAB005_20170705_001.txt | 50 | 264465 | 10132695114 | 5 | PBW5001 | MC517193…712 | 0 | 100.56 | 2017-06-15 | 16:55 | 2017-07-04 | NAB4321 | 1236
| 50 | 264465 | 10111283197 | 5 | PBP5002 | MC552387…005 | 0 | 50 | 2017-07-02 | 8:54 | 2017-07-04 | NAB1445 | 1236
NAB005_20170705_002.txt | 50 | 264465 | 10132695114 | 5 | PBW5001 | MC517193…712 | 0 | 100.56 | 2017-06-15 | 16:55 | 2017-07-04 | NAB4321 | 1236
| 50 | 264465 | 10111283197 | 5 | PBP5002 | MC552387…005 | 0 | 50 | 2017-07-02 | 8:54 | 2017-07-04 | NAB1445 | 1236
NAB005_20170705_003.txt | 50 | 264465 | 10132695114 | 5 | PBW5001 | DI657044…269 | 0 | 80 | 2017-06-15 | 16:55 | 2017-07-04 | NAB4863 | 1236
| 50 | 264465 | 10111283197 | 5 | PBP5002 | VI984601…453 | 0 | 45 | 2017-07-02 | 8:54 | 2017-07-04 | NAB2274 | 1236
| 50 | 264465 | 10149782103 | 5 | PBP5002 | JC567953…940 | 0 | 78 | 2017-07-02 | 8:54 | 2017-07-04 | NAB5271 | 1236
| 50 | 264465 | 10103224118 | 5 | PBP5002 | MC563283…689 | 0 | 28 | 2017-07-02 | 8:54 | 2017-07-04 | NAB6026 | 1236
NAB005_20170705_004.txt | 50 | 264465 | 10132695114 | 5 | PBW5001 | JC434713…034 | 0 | 80 | 2017-06-15 | 16:55 | 2017-07-04 | NAB5817 | 1236
| 50 | 264465 | 10111283197 | 5 | PBP5002 | DI506206…696 | 0 | 45 | 2017-07-02 | 8:54 | 2017-07-04 | NAB9853 | 1236
| 50 | 264465 | 10149782103 | 5 | PBP5003 | JC740602…458 | 0 | 78 | 2017-07-02 | 34:26 | 2017-07-04 | NAB2205 | 1236
| 50 | 264999 | 10100540128 | 5 | DPP0031 | VI680662…953 | 0 | 65.6667 | 2017-07-03 | 35:26 | 2017-07-05 | NAB4242 | 1236
| 50 | 264999 | 10103265129 | 5 | API003212 |  | 3 | 53.3333 | 2017-06-20 | 21:55 | 2017-07-06 | NAB4157 | 1236
| 50 | 264465 | 10103224118 | 5 | PBP5004 | JC512429…008 | 0 | 41 | 2017-07-02 | 8:17 | 2017-07-07 | NAB3839 | 1236
| 50 | 264999 | 10106438137 | 35 | BPYNAB05194155795842 |  |  | 45 | 2017-06-08 | 18:40 | 2017-07-08 |  | 1236
| 50 | 264465 | 10103346119 | 25 | PBW5001 | JC526841…815 | 0 | 78 | 2017-06-30 | 29:03 | 2017-07-09 | NAB1979 | 1236
| 50 | 264465 | 10106955148 | 5 | PBW5004 | AM425539…957 | 0 | 111 | 2017-07-01 | 39:26 | 2017-07-10 | NAB8952 | 1236
| 50 | 264465 | 10132695114 | 5 | PBP5005 | VI611001…663 | 0 | 144 | 2017-07-05 | 49:49 | 2017-07-11 | NAB3123 | 1236
NAB005_20170705_005.txt | 50 | 264465 | 10132695114 | 5 | PBW5001 | JC434713…034 | 0 | 51 | 2017-06-15 | 16:55 | 2017-07-04 | NAB3713 | 167
| 50 | 264465 | 10111283197 | 25 | PBP5002 | DI506206…696 | 0 | 52 | 2017-07-03 | 8:54 | 2017-07-04 | NAB5883 | 1000
| 50 | 264465 | 10149782103 | 5 | PBP5003 | JC740602…458 | 0 | 53 | 2017-07-02 | 34:26 | 2017-07-04 | NAB8454 | 166
| 50 | 264999 | 10100540128 | 5 | DPP0031 | VI680662…953 | 0 | 54 | 2017-07-03 | 35:26 | 2017-07-05 | NAB9876 | 1000
| 50 | 264999 | 10103265129 | 5 | API003212 |  | 3 | 55 | 2017-06-25 | 21:55 | 2017-07-06 | NAB2363 | 1000
| 50 | 264465 | 10103224118 | 5 | PBP5004 | JC512429…008 | 0 | 56 | 2017-07-02 | 8:17 | 2017-07-07 | NAB5627 | 166
| 50 | 264999 | 10106438137 | 35 | BPYNAB05194155795842 |  |  | 57 | 2017-06-08 | 18:40 | 2017-07-08 | NAB9194 | 1000
| 50 | 264465 | 10103346119 | 25 | PBW5001 | JC526841…815 | 0 | 58 | 2017-06-30 | 29:03 | 2017-07-09 | NAB1646 | 1000
| 50 | 264465 | 10106955148 | 5 | PBW5004 | AM425539…957 | 0 | 59 | 2017-07-01 | 39:26 | 2017-07-10 | NAB7429 | 167
| 50 | 264465 | 10132695114 | 25 | PBP5005 | VI611001…663 | 0 | 60 | 2017-07-05 | 49:49 | 2017-07-11 | NAB6312 | 1000
NAB005_20170705_006.txt | 50 | 264465 | 10132695114 | 5 | DPP0031 | DI759996…555 | 3 | 60 | 2017-06-15 | 16:55 | 2017-07-10 | NAB5838 | 1000
| 50 | 264465 | 10111283197 | 5 | PBP5002 | AM707940…015 | 0 | 61 | 2017-07-03 | 8:54 | 2017-07-10 | NAB5889 | 1000
| 50 | 264465 | 10149782103 | 5 | PBP5003 | MC906676…460 | 0 | 62 | 2017-07-02 | 34:26 | 2017-07-10 | NAB6974 | 168
| 50 | 264999 | 10100540128 | 5 | PBW5001 | DI775036…124 | 0 | 63 | 2017-07-03 | 35:26 | 2017-07-10 | NAB5183 | 168
| 50 | 264999 | 10103265129 | 5 | API003212 | AM691986…468 | 3 | 64 | 2017-06-25 | 21:55 | 2017-07-10 | NAB5325 | 1000
| 50 | 264465 | 10103224118 | 35 | BPYNAB05194155795842 |  | 0 | 65 | 2017-07-02 | 8:17 | 2017-07-10 | NAB3825 | 168
| 50 | 264999 | 10106438137 | 5 | BPYNAB05194155795842 |  |  | 66 | 2017-06-08 | 18:40 | 2017-07-10 |  | 1000
| 50 | 264465 | 10103346119 | 25 | PBW5001 | AM476634…186 | 0 | 67 | 2017-06-30 | 29:03 | 2017-07-10 | NAB6436 | 1000
| 50 | 264465 | 10106955148 | 5 | PBW5004 | MC451047…596 | 0 | 68 | 2017-07-01 | 39:26 | 2017-07-10 | NAB4197 | 168
| 50 | 264465 | 10132695114 | 5 | PBP5005 | AM878310…466 | 1 | 69 | 2017-07-05 | 49:49 | 2017-07-10 | NAB7209 | 1000
NAB005_20170705_007.txt | 50 | 264465 | 10132695114 | 35 | PBP5007 | JC434713…034 | 0 | 70 | 2017-07-06 | 17:55 | 2017-07-10 | NAB5817 | CH | TEST_004
| 50 | 264465 | 10111283132 | 5 | PBP5007 | DI824811…358 | 0 | 71 | 2017-07-03 | 8:54 | 2017-07-10 | NAB9259 | REC
| 50 | 264465 | 10149782103 | 25 | PBP5008 | MC606308…164 | 0 | 72 | 2017-07-02 | 34:26 | 2017-07-10 | NAB8201 | 1000
| 50 | 264999 | 10100540128 | 5 | PBW5009 | JC901620…911 | 0 | 73 | 2017-07-03 | 35:26 | 2017-07-10 | NAB7849 | REC
| 50 | 264999 | 10103265129 | 35 | API003212 | DI458767…477 | 0 | 74 | 2017-06-25 | 21:55 | 2017-07-10 | NAB2014 | 1000
| 50 | 264465 | 10103224118 | 35 | PBW5010 | MC427920…160 | 0 | 75 | 2017-07-06 | 8:17 | 2017-07-10 | NAB6026 | CH? | TEST_003
| 50 | 264999 | 10106438137 | 5 | PBP5011 | MC909751…143 | 3 | 76 | 2017-06-08 | 18:40 | 2017-07-10 | NAB5955 | ADJ
| 50 | 264465 | 10103346119 | 5 | BPYNAB05194155795842 | JC907129…491 | 0 | 77 | 2017-06-30 | 29:03 | 2017-07-10 | NAB3453 | 1000
| 50 | 264465 | 10106955148 | 5 | BPYNAB05194155795842 |  | 0 | 78 | 2017-07-01 | 39:26 | 2017-07-10 | NAB3249 | 1000
| 50 | 264465 | 10111283197 | 35 | PBW5009 | JC567953…940 | 0 | 79 | 2017-07-06 | 49:49 | 2017-07-10 | NAB2274 | CH? | TEST_003
NAB005_20170705_008.txt | 50 | 264465 | 10132695114 | 5 | PBW5010 | JC434713…034 | 0 | 80 | 2017-07-06 | 17:55 | 2017-07-10 | NAB4984 | REC
| 50 | 264465 | 10149782103 | 35 | PBP5011 | DI824811…358 | 0 | 81 | 2017-07-03 | 8:54 | 2017-07-10 | NAB3395 | CH | TEST_003
| 50 | 264465 | 10149782103 | 25 | PBP5012 | MC606308…164 | 0 | 82 | 2017-07-02 | 34:26 | 2017-07-10 | NAB8451 | 1000
NAB005_20170705_009.txt | 50 | 264465 | 10132695114 | 5 | PBW5010 | AM709260…954 | 0 | 90 | 2017-06-15 | 16:55 | 2017-07-10 | NAB3298 | 1007 | WEB_REC
| 50 | 264465 | 10111283197 | 5 | PBP5011 | DI846216…195 | 0 | 91 | 2017-07-02 | 8:54 | 2017-07-10 | NAB3524 | 1007 | IVC_REC
| 50 | 264465 | 10149782103 | 5 | PBP5012 | AM817218…100 | 0 | 92 | 2017-07-02 | 34:26 | 2017-07-10 | NAB5483 | 1007 | IVC_REC
| 50 | 264999 | 10100540128 | 5 | DPP5013 | JC648715…747 | 0 | 93 | 2017-07-03 | 35:26 | 2017-07-10 | NAB7201 | 1007 | ERR
| 50 | 264999 | 10103265129 | 5 | API5014 | JC471860…843 | 0 | 94 | 2017-06-20 | 21:55 | 2017-07-10 | NAB4353 | 1007 | ERR
| 50 | 264465 | 10103224118 | 5 | PBP5015 | JC512429…008 | 0 | 95 | 2017-07-02 | 8:17 | 2017-07-10 | NAB2039 | 1007 | IVC_REC
| 50 | 264999 | 10106438137 | 35 | BPYNAB5016 |  |  | 96 | 2017-06-08 | 18:40 | 2017-07-10 | NAB5871 | 1007 | ERR
| 50 | 264465 | 10103346119 | 25 | PBW5016 | VI501343…854 | 0 | 97 | 2017-06-30 | 29:03 | 2017-07-10 | NAB9238 | 1007 | ERR
| 50 | 264465 | 10106955148 | 5 | PBW5017 | MC746265…405 | 0 | 98 | 2017-07-01 | 39:26 | 2017-07-10 | NAB5444 | 1007 | WEB_REC
| 50 | 264465 | 10132695114 | 25 | PBP5018 | VI518370…644 | 0 | 99 | 2017-07-05 | 49:49 | 2017-07-10 | NAB7784 | 1007 | ERR
NAB005_20170705_010.txt | 50 | 264465 | 10132695114 | 5 | PBW5010 | AM709260…954 | 0 | 90 | 2017-06-15 | 16:55 | 2017-07-10 | NAB1853 | 1007 | WEB_REC
| 50 | 264465 |  | 5 | PBP5011 | DI846216…195 | 0 | 91 | 2017-07-02 | 8:54 | 2017-07-10 | NAB6692 | 1007 | IVC_REC
| 50 | 264465 | 10149782103 | 5 | PBP5012 | AM817218…100 | 0 | 92 | 2017-07-02 | 34:26 | 2017-07-10 | NAB4199 | 1007 | IVC_REC
| 50 | 264465 |  | 25 | PBW5016 | VI501343…854 | 0 | 97 | 2017-06-30 | 29:03 | 2017-07-10 | NAB8862 | 1007 | ERR
| 50 | 264465 | 10106955148 | 5 | PBW5017 | MC746265…405 | 0 | 98 | 2017-07-01 | 39:26 | 2017-07-10 | NAB4347 | 1007 | WEB_REC
| 50 | 264465 | 10132695114 | 25 | PBP5018 | VI518370…644 | 0 | 99 | 2017-07-05 | 49:49 | 2017-07-10 | NAB4620 | 1007 | ERR
NAB005_20170705_011.txt | 50 | 264465 | 10132695114 | 5 | PBW5010 | AM709260…954 | 0 | 90 | 2017-06-15 | 16:55 | 2017-07-10 | NAB8704 | 1007 | WEB_REC
| 50 | 264465 | 10149782103 |  | PBP5011 | DI846216…195 | 0 | 91 | 2017-07-02 | 8:54 | 2017-07-10 | NAB6578 | 1007 | IVC_REC
| 50 | 264465 | 10106955148 | 5 | PBP5012 | AM817218…100 | 0 | 92 | 2017-07-02 | 34:26 | 2017-07-10 | NAB6235 | 1007 | IVC_REC
| 50 | 264465 | 10149782103 |  | PBW5016 | VI501343…854 | 0 | 97 | 2017-06-30 | 29:03 | 2017-07-10 | NAB2235 | 1007 | ERR
| 50 | 264465 | 10106955148 | 5 | PBW5017 | MC746265…405 | 0 | 98 | 2017-07-01 | 39:26 | 2017-07-10 | NAB5219 | 1007 | WEB_REC
| 50 | 264465 | 10132695114 | 25 | PBP5018 | VI518370…644 | 0 | 99 | 2017-07-05 | 49:49 | 2017-07-10 | NAB8179 | 1007 | ERR
NAB005_20170705_012.txt | 50 | 264465 | 10132695114 | 5 |  | AM709260…954 | 0 | 90 | 2017-06-15 | 16:55 | 2017-07-10 | NAB5175 | 1007 | WEB_REC
| 50 | 264465 | 10111283197 | 5 | PBP5011 | DI846216…195 | 0 | 91 | 2017-07-02 | 8:54 | 2017-07-10 | NAB5529 | 1007 | IVC_REC
| 50 | 264465 | 10149782103 | 5 | PBP5012 | AM817218…100 | 0 | 92 | 2017-07-02 | 34:26 | 2017-07-10 | NAB8762 | 1007 | IVC_REC
| 50 | 264465 | 10111283197 | 25 |  | VI501343…854 | 0 | 97 | 2017-06-30 | 29:03 | 2017-07-10 | NAB2072 | 1007 | ERR
| 50 | 264465 | 10106955148 | 5 | PBW5017 | MC746265…405 | 0 | 98 | 2017-07-01 | 39:26 | 2017-07-10 | NAB4068 | 1007 | WEB_REC
| 50 | 264465 | 10132695114 | 25 | PBP5018 | VI518370…644 | 0 | 99 | 2017-07-05 | 49:49 | 2017-07-10 | NAB9218 | 1007 | ERR
NAB005_20170705_013.txt | 50 | 264465 | 10132695114 | 5 | PBW5017 |  | 0 | 90 | 2017-06-15 | 16:55 | 2017-07-10 | NAB5271 | 1007 | WEB_REC
| 50 | 264465 | 10111283197 | 5 | PBP5011 | DI846216…195 | 0 | 91 |  | 8:54 | 2017-07-10 | NAB5035 | 1007 | IVC_REC
| 50 | 264465 | 10149782103 | 5 | PBP5012 | AM817218…100 |  | 92 | 2017-07-02 | 34:26 | 2017-07-10 | NAB6594 | 1007 | IVC_REC
| 50 | 264465 | 10111283197 | 25 | PBP5018 | VI501343…854 | 0 | 97 | 2017-06-30 |  | 2017-07-10 | NAB1719 | 1007 | ERR
| 50 | 264465 | 10106955148 | 5 | PBW5017 | MC746265…405 | 0 |  | 2017-07-01 | 39:26 | 2017-07-10 | NAB6376 | 1007 | WEB_REC
| 50 | 264465 | 10132695114 | 25 | PBP5018 | VI518370…644 | 0 | 99 | 2017-07-05 | 49:49 | 2017-07-10 |  | 1007 | ERR
NAB005_20170705_014.txt | 50 | 264465 | 10132695114 | 5 | PBW5017 |  | 0 | 90 | 2017-06-15 | 16:55 | 2017-07-10 | NAB5271 | 1007 | WEB_REC
| 50 | 264465 | 10111283197 | 5 | PBP5011 | DI846216…195 | 0 | 91 | 2017-07-01 | 8:54 | 2017-07-10 | NAB5035 | 1007 | IVC_REC
| 50 | 264465 | 10149782103 | 5 | PBP5012 | AM817218…100 |  | 92 | 2017-07-02 | 34:26 | 2017-07-10 | NAB6594 | 1007 | IVC_REC
| 50 | 264465 | 10111283197 | 25 | PBP5018 | VI501343…854 | 0 | 97 | 2017-06-30 |  | 2017-07-10 | NAB1719 | 1007 | ERR
| 50 | 264465 | 10106955148 | 5 | PBW5017 | MC746265…405 | 0 |  | 2017-07-01 | 39:26 | 2017-07-10 | NAB6376 | 1007 | WEB_REC
| 50 | 264465 | 10132695114 | 25 | PBP5018 | VI518370…644 | 0 | 99 | 2017-07-05 | 49:49 | 2017-07-10 |  | 1007 | ERR

## COMPOSE_NAB_dev (hidden)
| Record Type | L | Source Identifier | L | Transaction reference number | L | Payment Instruction Type | L | Transaction reference number 2 | L | Transaction reference 3 | L | Error Correction reason | L | Amount | L | Payment Date | L | Payment Time | L | Settlement date | L | Bank Transaction ID | L | Authorisation Code | L | Original Reference | L | Filler | L
|  |  | 0 |  |  |  | 0 | [5 empty] | 0 |  | 0 |  | 0 |  | 0
1 | 2 |  | 10 |  | 20 |  | 2 |  | 21 |  | 21 |  | 3 |  | 12 |  | 8 |  | 6 |  | 8 |  | 30 |  | 6 |  | 20 |  | 50
| 50 | 2 | 264465 | 6 | 1097510176 | 10 | 5 | 1 | PBW0887 | 7 | MC552350...849 | 21 | 0 | 1 | 100 | 3 | 2017-07-04 | 5 | 16:55 | 17 | 2017-07-04 | 5 | 886096 | 6 | 1236 | 4 |  | 0 |  | 1
| 50 | 2 | 0000264465 | 10 | 1097510176 | 20 | 05 | 2 | PBW0887 | 21 | MC552350...849 | 21 | 000 | 3 | 000000010000 | 12 | 20170704 | 8 | 165432 | 6 | 20170704 | 8 | 886096 | 30 | 1236 | 6 |  | 20 |  | 50
| 50 | 2 | 264465 | 6 | 1097510176 | 10 | 5 | 1 | PBW0887 | 7 | MC552350...849 | 21 | 0 | 1 | 100 | 3 | 2017-07-04 | 5 | 16:55 | 17 | 2017-07-04 | 5 | 886096 | 6 | 1236 | 4 |  | 0 |  | 1
| 50 | 2 | 0000264465 | 10 | 1097510176 | 20 | 05 | 2 | PBW0887 | 21 | MC552350...849 | 21 | 000 | 3 | 000000010000 | 12 | 20170704 | 8 | 165432 | 6 | 20170704 | 8 | 886096 | 30 | 1236 | 6 |  | 20 |  | 50
219
500000264465 109751017605PBW0887 MC552350...849 0000000000100002017070416543220170704886096 1236

## COMPOSE_NAB
| Record Type | Source Identifier | Transaction reference number (Customer Account Number) | Payment Instruction Type | Transaction reference number 2 | Transaction reference 3 | Error Correction reason | Amount | Payment Date | Payment Time | Settlement date | Bank Transaction ID | Authorisation Code | Original Reference | Filler | 1 | GENERATOR Bank Transaction ID | Masked card number GENERATOR
|  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
| 2 | 10 | 20 | 2 | 21 | 21 | 3 | 12 | 8 | 6 | 8 | 30 | 6 | 20 | 50
| 50 | 264465 | 169389 | 5 | PBW5017 | DI846216…194 | 0 | 250 | 2017-06-15 | 16:55 | 2017-07-10 | NAB9547 | 1007 | WEB_REC |  |  | NAB5373 | VI940169…575
| 50 | 264465 | 175107 | 5 | PBP5011 | DI846216…195 | 0 | 1000 | 2017-07-01 | 8:54 | 2017-07-10 | NAB3108 | 1007 | IVC_REC |  |  | NAB2076 | VI917606…185
| 50 | 264465 | 168652 | 5 | PBP5012 | AM817218…100 | 0 | 120 | 2017-07-02 | 34:26 | 2017-07-10 | NAB6332 | 1007 | IVC_REC |  |  | NAB9868 | VI857621…887
| 50 | 264465 | 10111283197 | 25 | PBP5018 | VI501343…854 | 0 | 97 | 2017-06-30 |  | 2017-07-10 | NAB1719 | 1007 | ERR |  |  | NAB2961 | VI941060…081
| 50 | 264465 | 10106955148 | 5 | PBW5017 | MC746265…405 | 0 | 94 | 2017-07-01 | 39:26 | 2017-07-10 | NAB6376 | 1007 | WEB_REC |  |  | NAB9851 | VI876199…902
| 50 | 264465 | 10132695114 | 5 | PBP5018 | VI518370…644 | 0 | 99 | 2017-07-05 | 49:49 | 2017-07-10 |  | 1007 | ERR |  |  | NAB3485 | VI834512…791
219 | 500000264465 0000016938905PBW5017 DI846216…194 0000000000250002017061516543220170710NAB9547 1007 WEB_REC
219 | 500000264465 0000017510705PBP5011 DI846216…195 0000000001000002017070108542320170710NAB3108 1007 IVC_REC
219 | 500000264465 0000016865205PBP5012 AM817218…100 0000000000120002017070210254120170710NAB6332 1007 IVC_REC
219 | 500000264465 1011128319725PBP5018 VI501343…854 0000000000097002017063000000020170710NAB1719 1007 ERR
219 | 500000264465 1010695514805PBW5017 MC746265…405 0000000000094002017070115255620170710NAB6376 1007 WEB_REC
219 | 500000264465 1013269511405PBP5018 VI518370…644 0000000000099002017070501484720170710 1007 ERR